## Sheet1
Modules and Key Activities | Team members | Outputs | Timeline | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Module 1 Preparation
1.1 Feasibility Assessment | (List names) | Completed table and decision on proceeding | Week 1 | bar: Week 1
1.2 Training Team Selection and Work Planning |  | Training Team selected and trained. Work plan completed | Week 1 | bar: Week 1
1.3 Monitoring and Evaluation |  | Key performance indicators and means of verification are identified to demonstrate the effectiveness of the training | Week 1 | bar: Week 1
Module 2 Scoping
2.1 Review of Existing Information, Policies and Guidelines |  | Literature Review Key Findings | Week 2 | bar: Week 2 to Week 3
2.2 Key informant interviews with rangers and the management body |  | Priority Human Rights Impacts & Capacity Building Areas Identified | Week 3 and 4 | bar: Week 4 to Week 5
Module 3 Training
3.1 The training plan |  | Training Plan and Course Outline | Week 5 | bar: Week 6
3.1 Adapting training materials with case studies |  | Training Materials with Context Specific Case Studies | Week 5 & 6 | bar: Week 6 to Week 7
3.2 Implementing training |  | Post Training Report & Assessments | Week 7 & 8 (30 rangers & management body stuff max. per cohort; 2 days of training per cohort) | bar: Week 8 to Week 9
3.3 Training report |  | As above | Week 9 | bar: Week 10 to Week 11
3.4 Plan for Follow-Up Training and Training of Trainers |  | Follow-Up Training Plan | Week 10 | bar: Week 11